## Where are we?
Server setup is OK.
Update system (github, zotero, database logic) is OK, but still needs work. Will be stabilized by the end of 2024.
Texts validation system is OK, but can made more thorough. This is a never-ending task, I will keep improving it until the end of the project, on the side.
Texts processing and display system is fragile. Will become more stable when I sort out the search system, by the end of 2025. I need to work on this one or two days a week, until the end of the project.
## Problems to address
Referencing and numbering system viz. pointing to specific locations in inscriptions. With what we have now, I cannot produce unique, human-readable references. We need to sort this out by mid-2025.
Metadata spreadsheets. They need to be stored in our git repositories for referencial integrity. They also need to be simplified. We will need to discuss this and to write some documentation. There is no urgency for now, I believe, so we could start working on this in 2026.
Many files do not follow our schema: Epigraphia Carnatica, diplomatic editions of manuscripts, and critical editions.
- I will do the necessary work for Epigraphia Carnatica (a few weeks or work).
- Diplomatic editions of manuscripts (28 texts) could be fitted to our system if people are willing to adapt them and if Daniel is OK for adapting the EGD. This would take a few months of work.
- Critical editions (20 texts) are structured very differently and would require a good year of work (counting work on the EGC, etc.). I do not think the extra effort is worth it for so few texts.
## New tasks
Writing the Tamil lexicon search system represents a few months of work. The logic is already sorted out. The most time-consuming task is to clean up the data, I cannot tell for now how much time it will take.
Writing the search system is the most complicated and time-consuming task. I need to think about it for the second half of this year, while doing other things. I should definitely start writing it from 2025 onwards, and keep working on it until the end of the project. We will probably have a working initial iteration in late 2025.
We need to be reasonable when assigning me ad hoc, one-off auxiliary tasks. Maybe at most one day a week for such tasks, so that I have enough time to work on the rest.
For Amandine’s project, I cannot give a good estimation for now, but I doubt we will have a deliverable until 2026.
We should also reserve half a year at the end of the project for me to write tests, fix bugs, and document the application’s behavior. Ideally, no new feature should be added at this stage.